## Safenet contingency Refuge
Safenet Live continuity plan - Corona Virus
https://www.gov.uk/government/publications/covid-19-stay-at-home-guidance/stay-at-home-guidance-for-people-with-confirmed-or-possible-coronavirus-covid-19-infection
All files and relevant documents stored in shared/safenet/slt2/covid-19 folder
Risk Rating | A- Likelihood | B Harm | Risk Rating | Residual Risk Rating
| 4 | 3 | 12 | 6 | Monitor & Review
Who is affected | Potential Scenarios & Impacts | Mitigating Actions | Owner | Actioned date
CONTAIN
Residents | Preventing the spread of infection to residents | Residents entering our service asked about revent travel outside the UK, dates and location | completed and incorporated in to referral process 28.02.20 | 28.02.20
Staff & residents | Preventing the spread of infection within the refuge with existing residents & staff | Hand Sanitisers at entrances of all Refuges, purchase wipes, sprays for disinfection. | JOC | 12.03.20
Residents | Preventing the spread of infection within the refuge with existing residents & staff | Give out soaps and additional cleaning products to residents give information in house meetings | TL's | 5.3.20
Staff & residents | Preventing the spread of infection within the refuge with existing residents & staff | Signs displayed in all refuges on hand wash protocols updates in staff meetings | TL's | 5.3.20
Staff and residents | Preventing the spread of infection within the refuge with existing residents & staff | Ensure all cotton towels removed from communal areas- paper towels only | SLT | 5.3.20
Staff & residents | Preventing the spread of infection within the refuge with existing residents & staff | Cleaning regime, duties and frequency to be discussed at meeting - SLT and cleaners | SLT | 5.3.20
Staff & residents | Preventing the spread of infection within the refuge with existing residents & staff | Support workers to clean door handles, switches , buttons whilst carrying out support checks | TL's | 5.3.20
Staff | Preventing the spread of infection between staff | Desks and equipment in office areas to be disinfected daily using disposable wipes | All staff | 5.3.20
Staff & residents | Preventing the spread of infection from staff or residents who have recently travelled | Produce risk assessment for staff and referrals/residents that have returned from travel outside the UK | SLT | 5.3.20
Staff | Preventing cross contamination | Donations - review which products would not be safe to accept as a donation- issue guidance | TLs | ongoing
Residents | Safeguarding | Consult Mum's in refuge to look at family support network that could help with children in the event of mum poorly. | TLS | 5.3.20
Staff & residents | Preventing the spread of infection to vulnerable staff | Produce list of residents & staff that would be vulnerable in the event of an outbreak in refuge | TL's | 5.3.20
Residents | Unable to purchase food items | Check stock of tinned & dried food | TLs | 13.03.20
Clients | Ensuring safeguarding & safety | Produce a safeguarding /safety plan around and individual safe accomodation plan re potential reduced service | Support Workers / TLs | ongoing
Staff | Preventing spread of infection between staff and from other locations | Review DAILY whether to carry out staff meetings or suspend- As of 13.03.2020 all non essential meetings cancelled with the exception of handovers. | SLT | 13.03.20
Staff & residents | Ensuring safeguarding & safety procedures are in place | Individual Isolation/lockdown/closure plan to be drawn up for each refuge | SLT & TLs | 13.03.2020
DELAY
Resident & Staff | If a resident tests positive for COVID-19 or has either high temperature or new continous cough | Isolate resident and follow direct.gov guidance on home isolation (see above link) | AM/TL | ongoing
Resident |  | Isolate resident in wing /safehouse | TL's | ongoing
Visitors | If a resident tests positive for COVID-19 or has either high temperature or new continous cough | Restricting visitors to essential only depending on risk to and from visitor | SLT | ongoing
Residents | Increase in COVID - 19 cases | Provide PPE where appropriate for isolated residents | TLs | ongoing
Residents | Increase in COVID - 19 cases | Plan for collection of residents in isolation medications from chemists | TLs | ongoing
Staff | Increase in COVID - 19 cases | Reduced staffing - minimum staffing a site can operate is 2 , look at group sharing staff Delphi/Safenet/Acorn | SLT | ongoing
Staff | Increase in COVID - 19 cases | Review DAILY whether to carry out group work sessions or suspend- Group work cancelled at all sites 17.03.2020 | TLs | 17.03.2020
Staff & residents | Increase in COVID - 19 cases | Follow PHE Guidance on accepting new admissions at a site with spaces but has cases of residents either confirmed COVID-19 or self isolating | SLT | ongoing
Staff & residents | Increase in COVID - 19 cases | Refer to individual safe accomodation plans for each resident | TLS | 13.03.2020
Staff & Residents | Increase in COVID - 19 cases | Agree which staff can home work where appropriate | SLT | 17.03.2020
Staff & Residents | Increase in COVID - 19 cases | Refer to individual refuge isolation/lockdown/closure plan |  | 13.03.2020
Staff | Increase in cases in the local area | Staff that work in the community to move to telephone or email based support, no home visits, revisit safety planning and RIC reviews, regular client check ins. | AM/TL | 17.03.2020
Staff & residents | Increase in cases in the local area | Communal areas at Janes Place and Preston refuge closed as from 17.03.2020, in all other communal refuges clients should be advised to sit 2 meters apart and observe handwashing protocols. | AM/TL | 17.03.2020
Residents | Increase in cases in the local area | Emergency plans completed for all residents to identify safety needs, help required and their arrangements that could be put in place | AM/TL | 18.03.2020
Agencies | Increase in COVID - 19 cases | LCC Zoom provider call - re PPE, Finance, contracts, public health- slides in COVIS-19 file on shared SLT2 - further calls scheduled weekly by Helene Cooper & service updated completed also stored in Covid-19 file | Rachel Wade & Alex Atkinson | 19.03.2020
Schools | Increase in COVID - 19 cases | School closures announced , last day of school open 20.3.2020- key worker guidance communicated to staff | AM/TL | 20.3.2020
Staff | Increase in COVID - 19 cases | Recuitment advert updated to include all sites for relief staff - HR completed | Rachel Wade & Alex Atkinson | 19.03.2020
Staff & residents | Increase in COVID - 19 cases | Government guidance changed re staying at home, working from home where possible | For information purposes | 23.03.2020
Staff & residents | Increase in COVID - 19 cases | LDAF Meetings conducted weekly via Zoom | Rachel Wade & Alex Atkinson | 24.03.2020
Staff | Increase in COVID - 19 cases | Home working plan updated and implemented- see Covid -19 file in shared SLT 2 | Alex Atkinson | 23.03.2020
Staff & residents | Increase in COVID - 19 cases | Lauren Hartley emailed re updated high risk category guidance updated over the weekend, staff and residnt plans updated to reflect this | Lauren Hartley | 23.03.2020
Agencies | Increase in COVID - 19 cases | Letter to agencies providing current service update | Alex Atkinson | 23.3.2020
Staff | Increase in COVID - 19 cases | Skeleton staffing structure agreed and implemented 25.3.2020, new staffing schedules created - stored in Covid-19 file | Alex Atkinson | 23.3.2020
Residents | Increase in COVID - 19 cases | Letter to residents advising of new measures | Alex Atkinson | 24.3.2020
PPE | Increase in COVID - 19 cases | Issue raised re lack of PPE with Helene Cooper 24.3.2020, request for masks, aprons and gloves submitted , advised by H Cooper order has been accepted delivery date to be confirmed. Some Ppe - golves masks, gel has been souced through Calico - Liz Dewell and Nicola Compton Hill | Alex Atkinson | 01.04.2020
Residents | Increase in COVID - 19 cases | 2nd letter issued to residents due to some non compliance re staying at home guidance | Helen Gauder | 29.3.2020
Residents | Increase in COVID - 19 cases | 3rd letter issued to residents due to some non compliance re staying at home guidance in readiness for Easter Weekend , posters displayed at all entrances and noticeboards | Helen Gauder | 08.04.2020
PPE | Increase in COVID - 19 cases | Delivery of PPE from Nicola Crompton Hill due 03.04.2020 - 8 boxes of gloves and 500 masks, no aprons available | Rachel Wade & Alex Atkinson | 03.04.2020
Residents & staff | Increase in COVID - 19 cases | Group delivery commenced via Zoom, tablets received . Michelle holding training session via Zoom with licence logon to ensure added layer of security | Michelle Walsh | 08.04.2020
Residents & staff | Increase in COVID - 19 cases | Whoson application working and tested, staff rotas to be produced and traning given. Live chat will provide additional referral mechanism for Lancashire Refuges. | Alex Atkinson & Miranda Hawtrey | 08.04.2020
PPE | Increase in Covid-19 | Delivery of PPE and cleaning products from Calico & LCC | Rachel Wade & Alex Atkinson | 14.4.2020
Staff & referrals | Increase in COVID - 19 cases | Live chat launched 14.4.2020 | Alex Atkinson & Miranda Hawtrey | 14.4.2020
All | Increase in COVID - 19 cases | Government announced extension of lockdown for 3 weeks | All | 16.04.2020
Staff | Increase in COVID - 19 cases | Email to staff from AA re Keeping safe and reducing spread of Covid-19. Reitterated previous guidance and measures and also NEW mesure for staff to bring a pair of indoor shoes to be worn only in the refuge. | Alex Atkinson | 16.04.2020
Safehouses | Increase in Covid-19 | Safehouses available additional 6 in total- Burnley and Rochdale as move on, for isolation and manage additional referrals | Gill Taylor | 16.04.2020
Safehouses | Increase in Covid-19 | Safehouse occupancy spreadsheet created and saved in shared/safenet/ safehouse availability & occupancy folder, 15 safehouses (14 Burnley and 1 Lancaster) | Rachel Wade and Paris Brotherton | 20.4.2020
Staff & Referrals | Increase in Covi-19 | Staff update sent re new Referral form created 24.4.2020 to incorporate Covid-19 guidance and questions , 14 days self isolation for new referals and staff to wear PPE when admitting new resident etc Testing avalable to staff and families and latest guidance | Helen Gauder | 24.4.2020
Residents | Increase in Cov-19 | RW raised if testing could be extended to residents to reduce risk of Covid in refuges, potentially reduce period of isolation needed and speed up referral intake. Helene Cooper from LCC also raised this with Public Health | Rachel Wade & Alex Atkinson | 24.4.2020
Staff | Increase in Covid-19 | PPE update on official guidance from Liz Dewell emailed to all Safenet and requested to print, laminate and display in each office | Rachel Wade | 30.4.2020
Staff | Increase in Covid-19 | Email communication to Safenet from H Gauder re change in process for admission and self isolation, well being and working Safehouses | Helen Gauder | 06.05.2020
Staff | Increase in Covid-19 | Email to staff from Alex Atkinson re guidance on cleaning and prep of Safehouses | Alex Atkinson | 07.05.2020
Residents | Increase in Covid-19 | Resident letter updated with new governement guidance on outdoow exercise no longer limited to 1 hour | Helen Gauder | 11.05.2020
Staff | Increase in Covid-19 | Email and guidance on Covid information and working safely - sent by James Macaree 13.05.2020 | Meeting with SLT on 20.5.2020 to discuss
Residents | Increase in Covid-19 | Email confirmation received from H Cooper (LCC)15.5.2020 re residents and children over 5 can be tested on site in refuge, request forms and process emailed, stored in Coivd 19 file on shared | Rachel Wade | 15.5.2020
Residents and staff | Increase in Covid-19 | Government guidance on Covid symptoms now include loss of sende of taste and smell | Rachel | 18.05.2020
Residents | Increase | First onsite Covid test requested for JP resident | Rachel | 19.05.2020
Residents and staff | Increase in Covid-19 | Covid symptoms now include loss of sense of taste and smell- added to referral form along with NHS number and admissions process to include Covid test | Rachel Wade | to be finalised and issued 22.05.2020
Residents and staff | Increase in Covid-19 | Covid test request form , example of completed form , process for testing created | Rachel Wade | to be finalised and issued 22.05.2020
Staff | Increase in Covid-19 | All sites now at full staffing, additional IT purchased so spare rooms now utilised as additional office space to meet social distancing requirements, each of the additional office spaces have cleaning stations and PPE stocks | Alex Atkinson | 25.05.2020
Note on E11: Rachel Wade: likelihood 2, harm 3 2x3=6

## Risk Rating Matrix
Col (A) - Likelihood of Injury or Hazard | Col (B) - Severity of Injury or Hazard | Who Could Be Affected
1. Improbable - (Extremely Unlikely To Occur) | 1. Minor (No First Aid Required) | Operators
2. Remote (Small Chance Of Occurring) | 2. Harmful (Minor First Aid Required) | Maintenance / Quality
3. Occasional (Could Occur Sometime) | 3. Critical (Serious Fractures, Burns, L.T.A.) | Contractors
4. Probable (Unsurprised If It Happened) | 4. Severe (Amputations, Loss Of Eyesight) | Visitors
5. Frequent (Almost Certain To Happen) | 5. Catastrophic ( Fatality, Explosions Etc) | Special Cases (Pregnant Worker/Young People Under 18)

## Safenet contingency Community
Safenet Live continuity plan - Corona Virus
Who is affected | Potential Scenarios & Impacts | Mitigating Actions | Owner | Actioned date
CONTAIN
Staff & Clients | Preventing the spread of infection between staff & clients | Hand Sanitisers at entrances of all offices, purchase wipes, sprays for disinfection. | TLs | 10.3.20
Staff & Clients | Preventing the spread of infection between staff | Signs displayed in all offices on hand wash protocols updates in staff meetings | TL's | 5.3.20
Staff and Clients |  | Ensure all cotton towels removed from communal toilets and handwashing facilties paper towels only |  | 5.3.20
Staff & Clients |  | Cleaning regime, duties and frequency to be discussed at meeting - SLT and cleaners | SLT | 5.3.20
Staff & Clients |  | Staff to clean door handles, switches , buttons whilst carrying out support checks | TL's | 5.3.20
Staff & Clients |  | Desks and equipment in office areas to be disinfected daily using disposable wipes | All staff | 5.3.20
Staff & Clients | Preventing the spread of infection to and from clients | Review Personal Risk Assessement for staff and referrals/that have returned from travel outside the UK | SLT | 5.3.20
Clients | Ensuring safeguarding & safety | Produce a safeguarding /safety plan around potential reduced service | Support Workers & TLS | 17.03.2020
Staff | Preventing spread of infection between staff and from other locations | Review DAILY whether to carry out staff meetings or suspend- As of 13.03.2020 all non essentai lmeetings cancelled with the exception of handovers | SLT | 13.03.2020
Staff & Clients | Preventing the spread of infection | Produce list of staff that would be vulnerable in the event of an outbreak in office | TL's | 5.3.20
DELAY
Staff | Increase in cases in the local area | Review DAILY whether to carry out group work sessions or suspend- Group work cancelled at all sites 17.3.2020 | TLs SLT | 17.03.2020
Staff | If presenting with COVID-19 symptoms | Self Isolate as per direct.gov guidance | AM/TL
Staff & Clients | Member of staff or client tests postive for COVID-19 | Guidance issued around home working arrangements, Non frontline staff could work from home | SLT | 17.03.2020
Staff | Member of staff or client tests postive for COVID-19 | Reduced staffing - minimum staffing a site can operate is 2 , look at group sharing staff Delphi/Safenet/Acorn | SLT
Staff | Increase in cases in the local area | Staff to contact community based clients and advise them that we will now be supporting via phone or email | AM/TL | 17.03.2020
Staff | Increase in cases in the local area | Staff to move to telephone or email based support, no home visits, revisit safety planning and RIC reviews, regular client check ins. | AM/TL | 17.03.2020

## Safeguarding
No of residents Isolating | Location | Childcare required | No of children isolating | Mitigating Actions | Owner | Actioned date | Safeguarding Measures to consider
x2 pregnant residents | OH | N/A | N/A | Staff to inform of current updated guidelines for | CYP | 17.03.20 | Safeguarding Measures To Consider:
|  |  |  | pregnant women and to ascertian if the wish to | Workers |  | Single Adults:
|  |  |  | self-isolate. |  |  | Where residents are identified in the ‘vulnerable’ or ‘high risk’ category, staff to provide updated government guidelines around social isolation for up-to 12 weeks.
Staff to support parents to identify family and friends who may be able to care for their children should they become unwell and need to be isolated.
x1 child unwell (not COVID | Preston | N/A | 1 adult x3 children | Resident currently self-isolating, staff provided | Lucy | 17.03.20 | Where a parent becomes unwell and they have no childcare, staff will contact Children’s Social Care Duty Team to look at temporary alternative arrangements.
related) however immune |  |  |  | milk/toiletries/toys and communal areas have | Candy |  | Where families are already involved with Children’s Social Care, this will need to be shared with the appointed social worker, to look at alternative childcare arrangements.
system low so advised to |  |  |  | been closed. |  |  | Where children are displaying signs of being unwell or as classed as ‘high risk, the whole family will need to self-isolate. Staff to prepare activity packs for the children, which will include:
isolate by 111. | [6 empty] | - Refuge phone numbers for the office and mobile phone in case they need something in the flat or something has happened to mum – children’s workers to go through this with children
- A guide to phoning 999 in case of an emergency i.e. in case mum becomes really unwell and needs immediate medical attention – Children’s workers to go through this with children
x2 pregnant women | Preston | N/A | N/A | Staff to inform of current updated guidelines for | Sarah Blackston | 17.03.20 | - Games in the pack, such as finding a grid for snakes and ladders and laminating them. Tthese games to be looked at with mum and children so that they know how to use them if they do have to self isolate.
|  |  |  | pregnant women and to ascertian if the wish to |  |  | - Packs for children for learning – word searches, maths such as sums, writing poems etc and putting a competition on it for them to work together and the best poem wins – they hand it in after being isolated
|  |  |  | self-isolate. |  |  | - Putting toys in the packs for the children are occupied
- Story books (make them age appropriate and is mum able to help reading)
x1 adult kindney infection, | Preston | Yes - Staying with grand | N/A | Staff supporting with accessing food/toiletries | Lucy Candy | 17.03.20 | - Putting some films in the packs and try to source dvd players, Xboxes or play stations so that they can use them for films or games
immune system low and |  | mother |  | and checks done via phone |  |  | - A guide to staying calm and what to do when feeling anxious.. We could then place ways of dealing with feeling worried and anxious such as distraction techniques – i.e. having a bath, listening to some music, doing some yoga exercises, dancing or through creative activities.
advised by hosiptal to self | [6 empty] | - Plain paper and colouring pens/pencils
isolate
Where the impact of isolation becomes distressing for both parent/child, staff to consider allowing confined use of the play room, to be thoroughly cleaned afterwards.
x1 adult pneumonia | Rochdale | N/A | N/A | Staying with sister, staff completed safety plan, | Tori O'Callaghan | 17.03.20 | In extreme cases, for large families or where there are additional concerns such as child protection, mental health, parenting difficulties; SafeNet to look at vacating several safehouses for families who need to isolate.
advised to self isolate |  |  |  | will make contact x1 week |  |  | Additional Safeguarding Factors to consider:
-Where a child is seen to be displaying signs of being unwell and parents continue to access the community, staff to inform and educational/childcare provider that they may be attending.
1x pregnant resident | Rochdale | N/A | N/A | Staff to inform of current updated guidelines | Tori O'Callaghan | 17.03.20 | -Where an adult/child becomes unwell and is self isolations, staff to close communal areas of Refuge.
for pregnant women and to ascertain if they
wish to self-isolate
x1 sickness - self isolating | Lancaster | N/A | N/A | Staff supporting with food/toiletries and support | Nicky Holt | 17.03.20
no COVID symtpoms |  |  |  | checks via phone
1x diabetic-self isolating | Rochdale | N/A | N/A | Staff supporting with food/toiletries and support | Tori O'Callaghan | 17.03.20
checks via phone
1x diabetic/asthma | Rochdale | N/A | N/A | Staff supporting with food/toiletries and support | Tori O'Callaghan | 17.03.20
checks via phone
1x child COVID symptoms | SafeHouse | N/A | Mother and Child self- | In safehouse, so no access to Refuge. Staff to | Paris Brotherton | 17.03.20
sent home from school with | Burnley |  | isilating for 14 days | support with food/toiletires etc left at the door.
high temp/cough |  |  |  | Daily phone support/check ins. No medication.
NO CSC.
Please note - daily updates completed in safenet/SLT2/ Covid -19 file from 18.03.2020- for staff and residents
Daily conference calls with SLT team 18.03.20-02.04.20 and Monday, Weds and Friday 03.04.20 onwards

## Other links
| : COVID-19 guidance for VCSE sector |  | Click in yellow areas below to access hyperlinks
ok | · Generic guidance link: https://www.gov.uk/government/collections/coronavirus-covid-19-list-of-guidance
10th march | o Guidance for employers and businesses (which would apply regardless of sector): https://www.gov.uk/government/publications/guidance-to-employers-and-businesses-about-covid-19
o Decontamination in non-healthcare settings covers what to do if a confirmed case of COVID-19 has visited any non-healthcare setting: https://www.gov.uk/government/publications/covid-19-decontamination-in-non-healthcare-settings/covid-19-decontamination-in-non-healthcare-settings
Womens Aid contingency plan |  | https://mcusercontent.com/352a5d9f70ad29212c221f6fd/files/317b1d4a-d01f-479e-9fe1-316b32debf6e/Contingency_plan.pdf

## Calico Group actions
Our Group Approach
Our overall approach is to be calm, follow official guidance, be aware of the issues, make appropriate plans and generally do the right thing. While we hope it will be business as usual, we are seeing some challenges already. All teams need to review their business continuity plans. At a Group level we have agreed:
Sick Pay - We have agreed an approach to sick pay and will be paying full sick pay for contracted members of staff who self isolate following official guidance even if they are not contractually entitled to it. Also if staff are off sick with the actual virus, we will pay full sick pay for at the least the first two weeks even if they are not contractually entitled it. This is to ensure that staff members do not feel like they need to come in because they would only get statutory sick pay. We will keep this under review but most staff members would be entitled to this anyway. If you are unsure about this, then please check with HR.
Special Leave – We have an approach ready to announce for things like school closures – We will confirm our position as and when this happens. We aim to get the balance right between being a supportive employer and ensuring we can deliver our services.
Staff with underlying health conditions – This can be agreed on a case by case basis by managers, if you are unsure speak to HR
Home working – We are keeping under review the capacity for working from home and our approach to home working on a weekly basis.
Supply Issues - We are aware of some potential supply and material shortages – we are keeping an eye on this.